## Sheet1
	DESIGN AND MANUFACTURE OF A SYRINGE PUMP – GANTT CHART
WEEK NO	2	3	4	5	6	7	8	9	10	11
	12/10/20	19/10/20	26/10/20	02/11/20	09/11/20	16/11/20	23/11/20	30/11/20	07/12/20	14/12/20
OBJECTIVES
Challenge Week – Tasks on JIRA
Write simple pump program in Python
Build Syringe Pump v1
Testing Flow Rate with different motors
Testing Microstepping effect on accuracy
Modify STL files for Lynch additions
Incorporate limit switches on either end
Work on kivy touchscreen UI
Write backend code to interact with UI
Modify STL files for dual pump system
Print and build Syringe Pump V2
Design simple clamp to attach 2 pumps together
Update UI and backend code to support 2 pumps
Work on Bluetooth serial protocol for Android
Build basic UI for Syringe Pump Android App
Prepare for Oral Presentation